## Sheet1
project plan
Sprint# | life cycle | Task Name | Responsible | Start | End | Days | Status
1 |  | (Login & registration activities ) | kareem | 2018-03-10 | 2018-03-16 | 7 | in progress
1 | analysis | gathering requirements for login interface and it's component | youssef | 2018-03-10 | 2018-03-10 | 1 | complete
|  | gathering requirements for registration interface and it's component | marina | 2018-03-10 | 2018-03-10 | 1 | complete
| design | design sketches for login interface and it's component | alaa | 2018-03-11 | 2018-03-11 | 1 | complete
|  | design sketches for registration interface and it's component | alaa | 2018-03-11 | 2018-03-11 | 1 | complete
|  | determine design's material | marina | 2018-03-12 | 2018-03-12 | 1 | complete
|  | design customer&fixer tables | youssef | 2018-03-12 | 2018-03-12 | 1 | complete
| implementation | impelement customer&fixer authentication | mahmoud | 2018-03-13 | 2018-03-13 | 1 | complete
|  | create customer&fixer tables in database | kareem | 2018-03-14 | 2018-03-14 | 1 | complete
|  | implement login interface and it's component | alaa | 2018-03-15 | 2018-03-15 | 1 | complete
|  | implement registeration interface and it's component | mahmoud | 2018-03-16 | 2018-03-16 | 1 | complete
| test | test login & registeration activities | kareem & youssef | 2018-03-15 | 2018-03-16 | 2 | complete
2 |  | (fixer profile & it's fragments) | youssef | 2018-03-17 | 2018-03-28 | 12 | in progress
2 | analysis | gathering requirements for fixer profile and it's component | marina | 2018-03-17 | 2018-03-17 | 1 | complete
|  | gathering requirements for order fragment and it's component | youssef | 2018-03-17 | 2018-03-17 | 1 | complete
| design | design sketches for fixer profile interface and it's component | alaa | 2018-03-18 | 2018-03-18 | 1 | complete
|  | design sketches fo order fragment and it's component | alaa | 2018-03-18 | 2018-03-18 | 1 | complete
|  | determine design's material | marina | 2018-03-19 | 2018-03-19 | 1 | complete
|  | design order table & new fields in fixer table | youssef | 2018-03-20 | 2018-03-20 | 1 | complete
| implementation | create order table & add fields in fixer table in database | mahmoud | 2018-03-21 | 2018-03-22 | 2 | complete
|  | implement fixer profile and it's component | kareem | 2018-03-23 | 2018-03-24 | 2 | in progress
|  | implement order fragment and it's component | kareem | 2018-03-25 | 2018-03-26 | 2 | in progress
|  | implement fixer profile for customer search | kareem | 2018-03-27 | 2018-03-28 | 2 | in progress
| test | test fixer profile activity and order fragment | mahmoud | 2018-03-26 | 2018-03-28 | 3 | in progress
3 |  | (customer profile) | marina | 2018-04-05 | 2018-04-13 | 9 | not started
3 | analysis | gathering requirements for customer profile and it's component | youssef | 2018-04-05 | 2018-04-05 | 1 | not started
| design | design sketches for customer profile interface and it's component | alaa | 2018-04-06 | 2018-04-06 | 1 | not started
|  | determine design's material | marina | 2018-04-07 | 2018-04-07 | 1 | not started
|  | design new fields in customer table | mahmoud | 2018-04-08 | 2018-04-08 | 1 | not started
| implementation | add fields in customer table in database | mahmoud | 2018-04-09 | 2018-04-09 | 1 | not started
|  | implement customer profile and it's component | mahmoud | 2018-04-10 | 2018-04-12 | 3 | not started
| test | test customer profile activity | kareem & youssef | 2018-04-12 | 2018-04-13 | 2 | not started
4 |  | (customer search activity) | mahmoud | 2018-04-14 | 2018-04-20 | 7 | not started
4 | analysis | gathering requirements for customer search interface | youssef | 2018-04-14 | 2018-04-14 | 1 | not started
| design | design sketches for customer search interface and it's component | alaa | 2018-04-15 | 2018-04-15 | 1 | not started
|  | determine design's material | marina | 2018-04-16 | 2018-04-16 | 1 | not started
| implementation | add fields in customer table in database | mahmoud | 2018-04-17 | 2018-04-17 | 1 | not started
|  | implement customer search activity and it's component | mahmoud | 2018-04-18 | 2018-04-19 | 2 | not started
| test | test customer search activity | kareem & youssef | 2018-04-20 | 2018-04-20 | 2 | not started