## Sheet1
Project Risk
| project name: | Home Fix |  |  |  |  | target start date: | 2018-03-03
| project number: | 1 |  |  |  |  | target end date: | 2018-03-31
| business owner: | khaled eltahan |  |  |  |  | cost center: | 20000
| project manager: | mahmoud abo saleh
Risk Id | Risk categories | Risk Description | Probability of impact (1-5) | likelihood of occuring | Risk Rating | Contingency Plan Required (Yes/No) | Risk Approach | Risk Response Summary | Risk Owner
1 | project execution | Insufficient resources to successfully complete the project. | 4 | 0.6 | 2.4% | Yes | Risk Avoidance | On Technology side : resources are involved with Core platform | youssef
2 | project execution | Insufficient days to implement fixer profile and it's fragments. | 5 | 0.75 | 3.75% | Yes | Acceptance | work core to handle this part | mahmoud